## Project Management
Project Implementation |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  | Remarks | Legend:
|  | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 10
System Design | Overall Design Framework | 2020-05-01 10: Project Submission |  |  | Completed
| Use Case Design | [17 empty] | On-going | bar: 2020-02-01 17 to 2020-02-01 24
| Business Understanding (2 data sources) | [17 empty] | Not Started | bar: 2020-03-01 2
| Data Understanding & Preparation (Frameworx) | [17 empty] | Concerns exist | bar: 2020-03-01 2 to 2020-03-01 16
Domain Modelling | bar: 2020-03-01 2 to 2020-03-01 23
Web UI Design & Deployment | bar: 2020-03-01 16 to 2020-04-01 13
Validation | bar: 2020-04-01 6 to 2020-04-01 13
Project Report | Executive Summary | bar: 2020-03-01 23 to 2020-04-01 13
Business Problem Background | bar: 2020-02-01 17 to 2020-02-01 24
Market Research (academic & business) | bar: 2020-03-01 23 to 2020-04-01 13
System Objectives & Success Measurement | bar: 2020-03-01 2 to 2020-03-01 23
Project Solution, Implementation, Performance | bar: 2020-03-01 9 to 2020-04-01 13
Conclusion - Findings & Recommendation | bar: 2020-04-01 20 to 2020-04-01 27
Appendix | Proposal | bar: 2020-02-01 24
User Guide | bar: 2020-04-01 20 to 2020-05-01 4
Mapped Functionalities against knowledge of Courses | bar: 2020-03-01 9 to 2020-03-01 23
List of Abbr. & Reference | bar: 2020-04-01 20
1-2 pages individual project report | bar: 2020-04-01 20 to 2020-05-01 4
Miscellaneous | bar: 2020-04-01 27
Video | System Modelling & Use Case Demo | bar: 2020-04-01 13 to 2020-04-01 27